## Schedule
Rivera Mechanical - Meadowbrook Terrace riser valve replacement - October 2026
Prepared 2026-09-18. Times are water OFF / water back ON (estimated).
Building | Date | Work | Units affected | Water off | Water on (est.) | Crew lead | Crew lead cell
Aspen House | 2026-10-14 | Replace domestic water riser shutoff valves | All units (one riser) | 08:00 | 12:00 | Elizabeth Morgan | 720-555-7535
Birch House | 2026-10-15 | Replace domestic water riser shutoff valves | All units | 09:00 | 13:00 | Elizabeth Morgan | 720-555-7535
Cypress House | 2026-10-20 | Replace domestic water riser shutoff valves | All units | 08:30 | 12:30 | Elizabeth Morgan | 720-555-7535
Dogwood House | 2026-10-21 | Replace domestic water riser shutoff valves | Units 101-118 (east riser) | 09:00 | 14:00 | Elizabeth Morgan | 720-555-7535
Dogwood House | 2026-10-22 | Replace domestic water riser shutoff valves | Units 119-136 (west riser) | 09:00 | 11:30 | Elizabeth Morgan | 720-555-7535
Elm House |  | No work - riser valves replaced 2024