## Burn
Cost code | Description | Budget | Spent | Committed | Remaining
WG-01 | General conditions | 119000
WG-02 | Demolition and abatement | 49000
WG-03 | Electrical | 125000
WG-04 | HVAC | 115000
WG-05 | Exhibit fabrication | 296000
WG-06 | Gallery lighting | 65000
WG-07 | AV and interactive media | 87000
WG-08 | Design and engineering fees | 98000
WG-09 | Permits and inspections | 7500
WG-10 | Owner contingency | 65000
Total

## POs
PO | Vendor | Cost code | Description | Status | Original amount | Approved change orders | Invoiced | Still committed
PO-2026-015 | Harbor & Finch Builders | WG-01 | General contractor fee and site supervision | Open | 110500
PO-2026-017 | Coastline Demolition & Abatement | WG-02 | Selective demolition, lead paint abatement | Closed | 42500
PO-2026-018 | Brightwire Electrical Contractors | WG-03 | Branch circuits, panel upgrade, exhibit power | Closed | 102000
PO-2026-021 | Brightwire Electrical Contractors | WG-03 | Exhibit case outlets (added scope) | Open | 7600
PO-2026-024 | Seaboard Mechanical | WG-04 | Gallery HVAC with humidity control | Open | 87000
PO-2026-025 | Keelhaul Exhibit Studio | WG-05 | Exhibit fabrication and installation | Open | 213000
PO-2026-028 | Lumenharbor Lighting | WG-06 | Track lighting and fixtures | Open | 59250
PO-2026-030 | Signal & Tide Media | WG-07 | Projection and touchscreen interactives | Open | 74000
PO-2026-031 | Northbeam AV Integration | WG-07 | Projection package (vendor replaced) | Cancelled | 57500

## Invoices
Invoice | Vendor | Date | PO | Cost code | Amount | Status
HF-9376 | Harbor & Finch Builders | 2026-02-27 | PO-2026-015 | WG-01 | 11050 | Posted
HF-7634 | Harbor & Finch Builders | 2026-03-28 | PO-2026-015 | WG-01 | 11050 | Posted
HF-8808 | Harbor & Finch Builders | 2026-04-27 | PO-2026-015 | WG-01 | 11050 | Posted
HF-4578 | Harbor & Finch Builders | 2026-05-27 | PO-2026-015 | WG-01 | 11050 | Posted
HF-5617 | Harbor & Finch Builders | 2026-06-26 | PO-2026-015 | WG-01 | 11050 | Posted
HF-2553 | Harbor & Finch Builders | 2026-07-26 | PO-2026-015 | WG-01 | 11050 | Posted
HF-9725 | Harbor & Finch Builders | 2026-08-27 | PO-2026-015 | WG-01 | 11050 | Posted
CDA-2208 | Coastline Demolition & Abatement | 2026-02-11 | PO-2026-017 | WG-02 | 25500 | Posted
CDA-6409 | Coastline Demolition & Abatement | 2026-03-15 | PO-2026-017 | WG-02 | 17000 | Posted
BW6180 | Brightwire Electrical Contractors | 2026-03-16 | PO-2026-018 | WG-03 | 35700 | Posted
BW8815 | Brightwire Electrical Contractors | 2026-05-09 | PO-2026-018 | WG-03 | 40800 | Posted
BW9541 | Brightwire Electrical Contractors | 2026-07-17 | PO-2026-018 | WG-03 | 19380 | Posted
BW2528 | Brightwire Electrical Contractors | 2026-07-08 | PO-2026-021 | WG-03 | 3800 | Posted
SM-6458 | Seaboard Mechanical | 2026-04-19 | PO-2026-024 | WG-04 | 26100 | Posted
SM-6328 | Seaboard Mechanical | 2026-06-11 | PO-2026-024 | WG-04 | 39150 | Posted
SM-4130 | Seaboard Mechanical | 2026-08-06 | PO-2026-024 | WG-04 | 34000 | Posted
KES-5769 | Keelhaul Exhibit Studio | 2026-05-19 | PO-2026-025 | WG-05 | 42600 | Posted
KES-3044 | Keelhaul Exhibit Studio | 2026-06-24 | PO-2026-025 | WG-05 | 46860 | Posted
KES-6451 | Keelhaul Exhibit Studio | 2026-08-19 | PO-2026-025 | WG-05 | 38340 | Posted
LH5712 | Lumenharbor Lighting | 2026-06-11 | PO-2026-028 | WG-06 | 23700 | Posted
LH2501 | Lumenharbor Lighting | 2026-06-15 | PO-2026-028 | WG-06 | 23700 | Void
LH6194 | Lumenharbor Lighting | 2026-08-15 | PO-2026-028 | WG-06 | 14812.5 | Posted
STM-8807 | Signal & Tide Media | 2026-08-18 | PO-2026-030 | WG-07 | 4172.87 | Posted
MPA-3133 | Marlow Pike Architects | 2026-02-11 |  | WG-08 | 7648.82 | Posted
MPA-2314 | Marlow Pike Architects | 2026-01-29 |  | WG-08 | 9336.29 | Posted
MPA-7410 | Marlow Pike Architects | 2026-07-13 |  | WG-08 | 17537.2 | Posted
MPA-9549 | Marlow Pike Architects | 2026-03-31 |  | WG-08 | 17201.11 | Posted
HSE-7871 | Holloway Structural Engineers | 2026-03-08 |  | WG-08 | 5034.7 | Posted
BLD-9071 | City of Tidewater Permits | 2026-02-16 |  | WG-09 | 3542.89 | Posted
INSP-6855 | City of Tidewater Permits | 2026-07-22 |  | WG-09 | 782.69 | Posted

## Change orders
CO | PO | Date | Description | Amount | Status
CO-01 | PO-2026-024 | 2026-06-03 | Added dehumidifier for ship-model cases | 12250 | Pending
CO-02 | PO-2026-025 | 2026-05-06 | Interactive tide table build-out | 26250 | Approved
CO-03 | PO-2026-025 | 2026-06-06 | Delete second graphics rail | -3500 | Approved
CO-04 | PO-2026-025 | 2026-07-21 | Replica figurehead upgrade | 12000 | Pending
CO-05 | PO-2026-025 | 2026-06-20 | Walnut veneer in lieu of paint | 4750 | Rejected