## Log
CO # | PO | Date | Description | Amount | Status
CO-01 | PO 024 | 2026-06-03 | Added dehumidifier for ship-model cases | 12250 | Pending
CO-02 | PO 025 | 2026-05-06 | Interactive tide table build-out | 26250 | Approved
CO-03 | PO 025 | 2026-06-06 | Delete second graphics rail | -3500 | Approved
CO-04 | PO 025 | 2026-07-21 | Replica figurehead upgrade | 12000 | Pending
CO-05 | PO 025 | 2026-06-20 | Walnut veneer in lieu of paint | 4750 | Rejected